## 📊 Dashboard
EVOLVE EDGE ¦ AI Risk Assessment Dashboard
Enterprise AI Governance Tracker · Auto-calculated from Assessment Tracker
Total AI Systems |  |  | High Risk Systems |  |  | Medium Risk Systems |  | Low Risk Systems | Overdue Reviews
Live count ↑ |  |  | Live count ↑ |  |  | Live count ↑ |  | Live count ↑ | Live count ↑
RISK SUMMARY BY DEPARTMENT | [6 empty] | HOW TO USE THIS TRACKER
Department | Total Systems | Low | Medium | High | Critical | Avg Score | 1. Open the '📋 Assessment Tracker' sheet
Finance | 0 | 0 | 0 | 0 | 0 | 0 | 2. Add each AI system as a new row (Row 5 onwards)
HR / People | 0 | 0 | 0 | 0 | 0 | 0 | 3. Fill in all columns — dropdowns guide valid values
Customer Service | 0 | 0 | 0 | 0 | 0 | 0 | 4. Risk Score auto-calculates (Likelihood × Impact)
Operations | 0 | 0 | 0 | 0 | 0 | 0 | 5. Status indicators update automatically via formulas
IT / Technology | 0 | 0 | 0 | 0 | 0 | 0 | 6. This Dashboard updates automatically as you add data
Legal / Compliance | 0 | 0 | 0 | 0 | 0 | 0 | 7. Use '📁 Risk Register' to log incidents & changes
Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 8. Review and update at least quarterly
STATUS INDICATOR LEGEND | [6 empty] | ⚠️ Do not delete rows 1–4 in any sheet
🟢 Low (1–4) |  | 🟡 Medium (5–12) |  | 🔴 High (13–25) |  | 🟣 Overdue | ⚠️ Protect sheets before distributing
Accept and monitor annually |  | Mitigate and monitor quarterly |  | Immediate action required |  | Review date has passed

## 📋 Assessment Tracker
EVOLVE EDGE ¦ AI Risk Assessment Tracker
Instructions: Fill one row per AI system. Columns D & E are mandatory. Risk Score (Col I) calculates automatically. Status (Col P) auto-updates.
Total AI Systems Registered:
# | AI System Name | Version / Model | Department | Business Owner | Technical Owner | Purpose / Use Case | Likelihood (1–5) | Impact (1–5) | Risk Score (Auto) | Risk Level | Risk Category | Mitigation Summary | Mitigation Status | Residual Risk | Review Status | Last Reviewed | Next Review Due | Notes / Evidence
1 | Customer Chatbot | v2.1 | Customer Service | Jane Smith | Tom Lee | Handles tier-1 support queries | 2 | 2 |  |  | Operational | Monitor intent confidence monthly | Active | Low | Current | 19/03/2026 | 17/06/2026 | Deployed Jan 2024
2 | Credit Scoring Model | XGB-3.4 | Finance | David Brown | Priya Patel | Automates loan approval decisions | 4 | 3 |  |  | Bias & Fairness | Fairness audit Q1; SHAP explainability layer active | In Progress | Medium | Current | 17/02/2026 | 18/05/2026 | FCA notified
3 | HR Screening Tool | ResumeScan AI | HR / People | Claire Moss | James Wu | Pre-screens CVs for shortlisting | 4 | 4 |  |  | Bias & Fairness | Re-weighted training data; human review for all declines | Completed | High | Current | 18/01/2026 | 18/04/2026 | Ethics board review pending
4 | Demand Forecasting | Prophet v1.2 | Operations | Mark Evans | Sara Kim | Predicts product demand for inventory | 2 | 3 |  |  | Model Robustness | Drift monitoring active; retrain threshold set at 5% MAPE increase | Active | Low | Due Soon | 19/12/2025 | 19/03/2026
5 | Fraud Detection | IsolForest-2 | Finance | David Brown | Priya Patel | Real-time transaction anomaly detection | 3 | 5 |  |  | Cybersecurity | Red-team quarterly; API auth enforced; kill-switch tested | Active | High | Current | 19/03/2026 | 17/06/2026 | PCI-DSS scope
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## 📁 Risk Register
EVOLVE EDGE ¦ AI Risk Register — Incident & Change Log
Log every risk event, model change, audit finding, or review action. Each row = one event.
# | Date | AI System | Event Type | Risk Category | Description | Severity | Reported By | Assigned To | Action Taken | Status | Root Cause | Resolution Date | Lesson Learned | Linked Risk Score | Sign-off
1 | 15/01/2025 | Customer Chatbot | Model Drift | Operational | Intent classification accuracy dropped from 91% to 83% after traffic spike | Medium | Tom Lee | Tom Lee | Retrained model on Q4 2024 data; re-deployed | Resolved | Training data did not reflect seasonal language shifts | 28/01/2025 | Implement automated drift alert at <85% accuracy | 9 | Jane Smith
2 | 03/02/2025 | Credit Scoring Model | Bias Finding | Bias & Fairness | Internal audit found 12% approval rate disparity between demographic groups | High | External Auditor | Priya Patel | Applied Fairlearn re-weighting; added SHAP output to decline letters | In Progress | Original training data over-represented one demographic segment | 28/02/2025 | Include fairness metrics in all future model validation packs | 9 | David Brown
3 | 20/02/2025 | HR Screening Tool | Ethics Review | Bias & Fairness | Ethics committee flagged CV screening model for potential age bias in shortlisting | High | Claire Moss | James Wu | Suspended auto-shortlisting; added human review step; retraining scheduled | Open | Model penalised career gaps disproportionately affecting older candidates |  |  | 20 | Ethics Committee
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23

## 📅 Review Calendar
EVOLVE EDGE ¦ AI System Review Calendar
Track scheduled review dates for all AI systems. Green = Current ¦ Amber = Due Soon ¦ Red = Overdue
AI System | Risk Level | Review Cycle | Q1 Review | Q2 Review | Q3 Review | Q4 Review | Q1 Status | Q2 Status | Q3 Status | Q4 Status | Annual Review | Reviewer | Notes
Customer Chatbot | Low | Annual | — | — | — | Dec 2025 | — | — | — | Due | Dec 2025 | Tom Lee
Credit Scoring Model | Medium | Quarterly | Mar 2025 | Jun 2025 | Sep 2025 | Dec 2025 | Completed | Scheduled | Scheduled | Scheduled | Dec 2025 | Priya Patel | FCA reporting linked
HR Screening Tool | High | Quarterly | Mar 2025 | Jun 2025 | Sep 2025 | Dec 2025 | Overdue | Scheduled | Scheduled | Scheduled | Dec 2025 | James Wu | Ethics board sign-off needed
Demand Forecasting | Low | Annual | — | — | — | Nov 2025 | — | — | — | Scheduled | Nov 2025 | Sara Kim
Fraud Detection | High | Quarterly | Feb 2025 | May 2025 | Aug 2025 | Nov 2025 | Completed | Scheduled | Scheduled | Scheduled | Nov 2025 | Priya Patel | Red-team Q2

## 📖 Reference
EVOLVE EDGE ¦ Reference Tables — Risk Matrix, Scales & Dropdown Lists
5×5 Risk Matrix (Likelihood rows × Impact columns) | [5 empty] | Valid Dropdown Values
| 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Critical | Department
5 Alm.Certain | 5 | 10 | 15 | 20 | 25 | Finance
4 Likely | 4 | 8 | 12 | 16 | 20 | HR / People
3 Possible | 3 | 6 | 9 | 12 | 15 | Customer Service
2 Unlikely | 2 | 4 | 6 | 8 | 10 | Operations
1 Rare | 1 | 2 | 3 | 4 | 5 | IT / Technology
Legal / Compliance
Legend: | [5 empty] | Marketing
Low (1–4): Accept & monitor annually | [5 empty] | Other
Medium (5–12): Mitigate & review quarterly
High (13–25): Immediate action required | [5 empty] | Risk Category
Bias & Fairness
Data Privacy
Model Robustness
Explainability
Operational
Legal & Compliance
Cybersecurity
Supply Chain
Other
Mit. Status
Not Started
In Progress
Completed
Overdue
Deferred
N/A
Review Status
Current
Due Soon
Overdue
Suspended
Severity
Low
Medium
High
Critical
Residual Risk
Low
Medium
High
Critical
Closed